## Slide 1: diap annual action plan 2026-2027

## Slide 2: Diversity and inclusion action plan (DIAP)
diap annual action plan 2026-2027
Our ongoing commitment to Equality, Diversity, and Inclusion in all our work is here.
The following actions will be completed by London Sport between April 2026 and March 2027, together comprising the second “annual action plan”, our DIAP.
These actions are intended to build on work already completed and will be embedded into our Work Area delivery plans and our Zoho project management tool to track and monitor progress.
Actions will be monitored on a regular basis through our EDI All Staff group, Trustee led EDI Sub-Committee, and our Senior Leadership Team.
Actions have been split into a) ongoing business as usual (BAU) activity, some of which has emerged as good practice from the first year of our DIAP and underpins our commitment to EDI, and b) shorter-term project-based activity that we’ll achieve through 2026 and 2027.
Actions continue to correspond to the “internal” and “external” objectives to ensure that London Sport is effectively implementing the DIAP.
This year’s plan also integrates recommendations from the GDEIB (Global Diversity, Equity & Inclusion Benchmarks) benchmarking exercise London Sport undertook in Spring 2026 with Diversity Marketplace.

## Slide 3: INTERNAL OBJECTIVES
DIAP ANNUAL ACTION PLAN 2026/2027

## Slide 4: DEMONSTRATING ORGANISATIONAL EDI EXCELLENCE: Our commitments
INTERNAL OBJECtIVES
Representation & Recruitment (IN 1)
We want our workforce to represent the diversity makeup of London, and we want our recruitment process to be free from bias to actively encourage applications from diverse backgrounds including from those outside the sport and physical activity sectors.
An inclusive experience for all staff in the workplace (IN 2)
We’re committed to creating an inclusive, open, and safe environment for colleagues to work and develop in. We will ensure that everyone feels accepted and valued for who they are with no judgement. London Sport is somewhere colleagues feel proud to work and enjoy their work environment and culture.
Staff knowledge, training, development and practice (IN 3)
We’re committed to ensuring that staff have excellent knowledge of equity/equality, diversity and inclusion, supported by a consistent offer of excellent targeted EDI training and development to support their continuous development and application of their EDI knowledge.
Use data to measure our progress and refine our practice (IN 4)
We’re committed to being an insight led organisation using data to monitor and evaluate our internal organisation progress on EDI. We aim to align with London's diverse demographics while integrating emerging trends to ensure our internal practices remain inclusive and forward-thinking.

## Slide 5: EXTERNAL OBJECTIVES
DIAP ANNUAL ACTION PLAN 2026/2027

## Slide 6: ESTABLISHING LONDON SPORT AS A LEADING ADVOCATE FOR EDI EXCELLENCE IN LONDON’S SPORT & Physical activity sector
EXTERNAL OBJECTIVES
Embedding EDI across all our workstreams with stakeholders (EX 1)
All our projects and programmes involve reaching, engaging and enabling Londoners in more deprived communities to move more. We are committed to co-produce any interventions with the real experts – people with lived experience of all protected characteristics, across all communities. We will do so with EDI at the heart. This means the people who ultimately benefit from these changes are alongside us and our stakeholders to ensure accessibility and inclusion is considered and implemented in every step.
To be recognised as EDI thought and practice leaders (EX 2)
London Sport is committed to becoming a leader in creating safe and welcoming environments for everyone to thrive, regardless of their background, race, gender, ethnicity, disability, religion, age or any other personal characteristic. We will work with organisations, clubs, and groups who share our values to tackling inequalities, to encourage all our partners to engage in continued EDI development, to ensure their knowledge and practice prioritises equality and diversity. We will advocate for inclusivity in sports clubs and organisations across London and will listen to the lived experiences of those in the communities in which we work.
Embed EDI Best Practice in Marketing and Communications (EX 3)
London Sport will follow best EDI practice principles in the design and production of its marketing and communication materials and will ensure that information can be made available in a range of formats.
Use data to measure our progress and refine our practice (EX 4)
London Sport leverages data as a key partner and influencer, driving progress on equality, diversity and inclusion across the sector. Through evidence-based insights, we will support stakeholders in embedding best practices and continuously refining approaches to meet evolving challenges.

## Slide 7: Behaviour Change we want to see

## Slide 8: INTERNAL Behaviour CHANGE
Behaviour change
London Sport aims to normalise EDI as a core, habitual way of thinking and acting - so that inclusion, equity and representation shape every decision, interaction and outcome across the organisation.
From:
‘EDI as a specialist function or initiative’
To:
‘EDI is everyone’s everyday responsibility and default way of working’
Notes: From ‘’EDI as a specialist function or initiative’
To ‘EDI is everyone’s everyday responsibility and default way of working’
What this means in practice:
1. Embedding EDI into every decision and action
2. Collective accountability by everyone across the organisation
3. Lived-experience-led design
4. Evidence-driven action
5. Actively challenging inequality

## Slide 9: EXTERNAL Behaviour CHANGE
Behaviour change
London Sport aims to influence and enable partners, communities and the wider sector to embed equity, inclusion and representation as standard practice – so that inclusive opportunities, experiences and outcomes are consistently delivered across London’s Sport and Physical Activity system.
From:
‘Inclusion is considered optional, additional, or targeted at specific groups’
To:
‘Inclusion is designed in from the outset and is a shared responsibility across the whole system’

## Slide 10: Ongoing business as usual (BAU) work
DIAP ANNUAL ACTION PLAN 2026/2027

## Slide 11: Ongoing / business as usual work (1)
Ref | ACTION | OWNER (Work Area) | DUE DATE | SUCCESS CRITERIA
BAU 1 (IN2) | Annually update the London Sport Awareness Calendar and deliver Awareness Activations for key dates: Awareness Activations 2026.pptx | EDI Core Group (Running LS) | Calendar updated Annually in December Date per event for Awareness Activations | Awareness Calendar updated and reflects events across a broad range of protected characteristics and themes. Deliver Awareness Activations which have Positive Staff feedback (>75% report events are relevant, inclusive and valuable). Connect events to House of Sport where possible for maximum value. Events improve London Sport staff confidence in relation to EDI awareness (measured through EDI Staff Survey).
BAU 2 (IN2) | Deliver the All-Staff EDI Group for 26-27. | EDI Chair (Running LS) | Date per meeting | Coordinate and facilitate group, meeting 8 weekly. Build in effective connection to other staff groups & House of Sport. Staff feedback indicates the group is relevant, inclusive, and valuable (>75% positive responses).
BAU 3 (IN3) | Creation of annual training plan for mandatory diversity and inclusion training for all staff, focusing on gaps shown through the EDI Staff Survey. Trustees & EDISC members also invited to attend. | HR Manager (Running LS) | Annually in July | Annual training plan has a specific EDI components to address gaps in employee knowledge, as identified by annual EDI staff survey & people survey. Improved employee confidence post training (measured through EDI Staff Survey).
BAU 4 (IN3) | Identify specific work areas for Activity Alliance placement to enhance London Sport's disability inclusion work, work plan subsequently developed, delivered and monitored. | Strategic Lead - Health (All Work Areas) | July 2026 | For example: LS staff upskilled to effectively integrate disability inclusion into the delivery of the LS strategy (measured through EDI Staff Survey).

## Slide 12: Ongoing / business as usual work (2)
Ref | ACTION | OWNER (Work Area) | DUE DATE | SUCCESS CRITERIA
BAU 5 (IN3) | Keep all staff up to date by providing updates on DIAP progress through: Themed Briefing (2 x annually), EDI Sub Committee and Board Updates (1 x annually). | EDI Core Group (Running LS) | Ongoing | Staff are up to date on our latest achievements on EDI and DIAP delivery and are aware of what work is planned.
BAU 6 (IN3) | Ensuring that updates and opportunities from the Active Partnership Network Race Equality Group are shared with all London Sport Staff. | EDI Chair CEO (Running LS) | Ongoing | Staff are aware of APN Race Equality work such as the Network for Ethnically Diverse Colleagues and training such as developing Race Literate Leaders.
BAU 7 (IN4) | Run EDI Staff Survey - review findings & share with staff. | Insight Manager (Data & Systems) | Annually in June/July | Survey completed. Reviewed by internal EDI groups. Shared with organisation via Annual TB.
BAU 8 (IN4) | Review data to inform decision making and EDI Direction – Benchmarking exercise, EDI Staff Survey, Staff Survey & any baseline metrics. | COO (Running LS) | Annually in June/July | Data review completed and findings presented to EDISC. At least two specific actions identified from the review and added to DIAP delivery.
BAU 9 (EX3) | Embed inclusive communications standards across all content ensuring communications are accessible to all audiences | Head of Comms and Activity Alliance Strategic Partnership Advisor (Advocacy & Influencing) | Ongoing | All staff are familiar with accessible comms tools and these continue to be used in all engagement with external stakeholders 100% of videos captioned and include subtitles All digital social media assets are accompanied by appropriate alt text.

## Slide 13: 26/27 PRIORITY ACTIONS
DIAP ANNUAL ACTION PLAN 2026/2027

## Slide 14: 26/27 PRIORITY ACTIONS (1)
Ref | ACTION | OWNER (Work Area) | DUE DATE | SUCCESS CRITERIA
26/27 1 (IN2) | Codify monitoring of flexible working and family-related decisions. Document how applications are reviewed, and how decisions are recorded. | COO and HR Manager (Running LS) | Mar 2027 | Documented monitoring process in place. Meets GDEIB benchmark 7.7, moving Category 7 from Level 3 to Level 4.
26/27 2 (IN2) | Document and publish progression pathway criteria, consulted upon with EDI Core Group. | HR Manager | Mar 2027 | Criteria published internally. Staff can self-assess readiness against criteria. Unsuccessful candidates can understand what they need to develop. Addresses GDEIB Category 5 evidence gap.
26/27 3 (IN2) | Document succession contingency for the EDI Chair role, including named cover for the parental leave period (June–September 2026). | EDI Chair, with EDI Core Group | Mar 2027 | Contingency arrangement documented in EDI Core Group Terms of Reference. Cover lead identified and briefed. Re-election and term extension process documented.
26/27 4 (IN2) | Document the job level classification framework once completed. | HR Manager (Running LS) | Mar 2027 | Documented framework provides objective evidence for GDEIB benchmarks 6.6 and 6.13. Used as the basis for consistent salary decisions.

## Slide 15: 26/27 PRIORITY ACTIONS (2)
Ref | ACTION | OWNER (Work Area) | DUE DATE | SUCCESS CRITERIA
26/27 5 (IN3/EX1) | Embed Equity, Diversity and Inclusion (EDI) within London Sport’s procurement and commissioning processes by introducing proportionate EDI-weighted contract award criteria in procurement policies, tender scoring matrices, and strengthening supplier diversity ie through membership of MSDUK (Minority Supplier Development UK). | COO (Running LS) | March 2027 | Procurement policy updated. Staff briefing delivered and recorded. All staff with procurement responsibilities have received the briefing within the year. All tenders include EDI as part of scoring criteria. Tender scoring matrix shows DEI weighting. Linked to the procurement work under EX 1. Evidences GDEIB benchmark 15.6 – 15.9; 15.11, and 15.13.
26/27 6 (EX2) | Proactively share London Sport's insight, learning, practice and expertise (including new developments in EDI and PA&S space) – through publication of case studies, insight reports, and practical toolkits, and speaker/panel opportunities, demonstrating inclusive programme design and delivery. | Head of Comms (Advocacy & Influencing) | March 2027 | Minimum of 2 insight reports, toolkits, or case studies published annually. EDI is a consideration across all reports and thought leadership work, even if not the main focus of the project. Contribute to panel sessions / external opportunities where relevant.
26/27 7 (EX2) | Develop our approach to incorporating lived experience into London Sport projects, leading to the creation of a standardised process for London Sport projects and identify at least two key pieces of work to which it will apply. | Heads of Insight/Impact and Learning and Head of Delivery (Impact & Learning) | March 2027 | Process is embedded into project planning & impact reporting Mechanisms such as community insight panels, co-production and structured engagement with underrepresented groups Staff feel confident using mechanisms identified (measured through staff survey). Evidence of programme or organisational changes directly informed by lived experience. Community participants report feeling their voice influenced decision-making.

## Slide 16: 26/27 PRIORITY ACTIONS (3)
Ref | ACTION | OWNER (Work Area) | DUE DATE | SUCCESS CRITERIA
26/27 8 (EX2) | Embed accessibility inclusion and culturally competent practice by: implementing minimum equality, diversity & inclusion standards for all London Sport events. Including developing a standardised checklist for events, programmes and engagement activities. | Head of Comms/Head of Delivery & EDI Core Group (Advocacy & Influencing) | March 2027 | Toolkit is developed. Toolkit is applied for Safeguarding in Sport Week 2027 and Festival of Learning. >85% of attendees / participants report events are inclusive and accessible.
26/27 9 (EX2) | Use cultural, religious and awareness days to amplify underrepresented communities and promote inclusive practice across London’s sport and physical activity sector, by identifying 2 community led story opportunities. | EDI Core Group & Head of Comms (Advocacy & Influencing) | March 2027 | At least 2 partner or community-led stories shared annually aligned to key EDI Calendar moments (e.g. Black History Month, Pride, Ramadan, Disability History Month). Representation of diverse communities across all comms.
26/27 10 (EX4) | Embed monitoring of external EDI impact into the Sport England annual reporting cycle, ensuring evidence is in place ahead of next GDEIB assessment. | Head of Impact and Learning (Impact & Learning) | March 2027 | External EDI evidence base in place. Aligned in SE reporting cycles. Provides Level 3 and Level 4 evidence in GDEIB Categories 12 and 13 at next assessment.